## Sheet1
# | Task Description | Environment
1 | Conduct infrastructure and architecture review to validate compatibility with Talend 8.x. | All
2 | Perform prerequisite backups for TAC database, SVN, and archive folder. | All
3 | Provision on-prem and cloud servers for Remote Engine installation. | DEV/TEST/UAT/PROD
4 | Open firewall ports between Talend Cloud and Azure. | All
5 | Installations and Configurations | DEV/TEST/UAT/PROD
5.1 | Install Talend 8.x Studio | DEV
5.2 | Install Nexus Repository | DEV
5.3 | Install and Configure Remote Engine | DEV/TEST/UAT/PROD
5.4 | Configure Talend Administration Center (TAC) | DEV/TEST/UAT/PROD
5.5 | Configure Talend Data Preparation | DEV/TEST/UAT/PROD
5.6 | Configure Talend Data Stewardship | DEV/TEST/UAT/PROD
5.7 | Configure TAC Database | DEV/TEST/UAT/PROD
6 | Migrate all jobs and code from Talend 7.3.1 to 8.x. | DEV
6.1 | Address deprecated components and compatibility issues during migration. | DEV
7 | Conduct unit testing for each migrated job to validate data ingestion. | DEV
8 | Deploy jobs into TEST TAC and perform SIT with results shared with CCA. | TEST
9 | Support UAT migration and run sample jobs for validation. | UAT
10 | Prepare CCB documentation and migration checklist. | All
11 | Design and build a reusable job for extracting metadata using Talend Cloud APIs. | DEV
12 | Update Tableau dashboards to point to new tables in the database. | All
13 | Provide training on new features of Talend 8.x to the CCA team. | All